## Sheet1
Analysis Group | Analysis Subgroup | Question/ Task | Subtask/ Detail | Primary Survey | Secondary Surveys | External Surveys | Author | Analytical Stage | Scheduled Completion | Next Steps
General | Data acquisition and preparation | Obtain Survey Data |  | FMWT |  |  | Tillotson | Complete
General | Data acquisition and preparation | Convert to flat .csv |  | FMWT |  |  | Tillotson | Complete
General | Data acquisition and preparation | Obtain Survey Data |  | STN |  |  | Tillotson | Complete
General | Data acquisition and preparation | Convert to flat .csv |  | STN |  |  | Tillotson | Complete
General | Data acquisition and preparation | Obtain Survey Data |  | SKT |  |  | Tillotson | Complete
General | Data acquisition and preparation | Convert to flat .csv |  | SKT |  |  | Tillotson | Complete
General | Data acquisition and preparation | Obtain Survey Data |  | 20mm |  |  | Tillotson | Complete
General | Data acquisition and preparation | Convert to flat .csv |  | 20mm |  |  | Tillotson | Complete
General | Data acquisition and preparation | Obtain Survey Data |  | SLS |  |  | Tillotson | Complete
General | Data acquisition and preparation | Convert to flat .csv |  | SLS |  |  | Tillotson | Complete
General | Data acquisition and preparation | Obtain Survey Data |  | EDSM |  | EDSM | Tillotson | Complete
General | Data acquisition and preparation | Convert to flat .csv |  | EDSM |  | EDSM | Tillotson | Complete
Gereral | Data acquisition and preparation | Integrate Datasets |  | All |  |  | Tillotson | Nearing completion
Evaluation of Existing Data | Regional Abundance Estimates | How are stations distributed across regions, depths and habitats? | GIS | FMWT | SKT, STN |  | Tillotson | Initiated |  | Meet with ICF GIS team
Evaluation of Existing Data | Regional Abundance Estimates | How are stations distributed relative to environmental gradients? |  | FMWT | SKT, STN
Evaluation of Existing Data | Regional Abundance Estimates | Which stations have least impact on abundance estimates/ uncertainty? |  | FMWT
Evaluation of Existing Data | Regional Abundance Estimates | Calculate estimates of abundance at Delta sub-regional scales | Index Method | FMWT | SKT, STN
Evaluation of Existing Data | Regional Abundance Estimates | Calculate estimates of abundance at Delta sub-regional scales | Raw Catch | FMWT | SKT, STN
Evaluation of Existing Data | Regional Abundance Estimates | Calculate estimates of abundance at Delta sub-regional scales | Desgin-based estimators | FMWT | SKT, STN
Evaluation of Existing Data | Catchability for species other than DS | Locate/generate fish catch selection curves | Species A | FMWT
Evaluation of Existing Data | Catchability for species other than DS | Locate/generate fish catch selection curves | Specis B | FMWT
Evaluation of Existing Data | Catchability for species other than DS | Calculate observed retention probability by length
Evaluation of Existing Data | Catchability for species other than DS | Quantify variation in catchability between species
Evaluation of Existing Data | Catchability for species other than DS | Quantify variation in catchability between surveys
Evaluation of Existing Data | Catchability for species other than DS | Quantify variation in catchability through time
Evaluation of Existing Data | Spatial Distribution of Species | Model relationships with covariates
Evaluation of Existing Data | Spatial Distribution of Species | Multivariate analysis of spatiotemporal patterns
Evaluation of Existing Data | Spatial Distribution of Species | Identify stations with high/low species diversity, catch rates, etc.
Evaluation of Existing Data | Spatial Distribution of Species | Generate station rankings based on multiple criteria
Evaluation of Existing Data | Long-Term Trends | Fit temporal trend models | Single survey trends | FMWT
Evaluation of Existing Data | Long-Term Trends | Fit temporal trend models | Combined survey trends | FMWT,STN,SKT
Evaluation of Existing Data | Long-Term Trends | Compare trends among regions |  | FMWT
Evaluation of Existing Data | Long-Term Trends | Explore variability in abundance estimates between regions and years |  | FMWT
Evaluation of Existing Data | Sampling Method Optimization | Evaluate the influence of # of tows |  | FMWT
Evaluation of Existing Data | Sampling Method Optimization | Evaluate the influence of tow duration |  | FMWT
Evaluation of Existing Data | Sampling Method Optimization | Evaluate representativeness of size distributions |  | FMWT